## Cover
THE UNITED REPUBLIC OF TANZANIA PRESIDENT’S OFFICE, e-GOVERNMENT AUTHORITY
DAIRE – DECENTRALIZED AI REPUTATION ENGINE.
WORK PLAN.

## Work Plan
Introduction:
DAIRE (Decentralized AI Reputation Engine) is a platform that links the lender systems of Financial Service Providers (CRDB, MoFinance and NMB), the national identity registry (NIDA), a Central System, an AI reputation model and a blockchain smart contract, so that customers who lack a formal credit history receive one trusted credit score that is shared with every lender they use.
MAIN ACTIVITY | SUB-ACTIVITIES | STATUS
REQUIREMENTS AND DESIGN | System Requirements Specification (SRS). | Completed.
| System Design Document (SDD) with architecture, data flow, ERD, use case and sequence diagrams. | Completed.
NIDA SYSTEM (Django + DRF) | Citizen registry database (Region, Citizen) and import of the 200-citizen dump. | Completed.
| Identity verification API (POST /api/v1/nida/verify/) and health check. | Completed.
| Trusted client IP allow-list (TRUSTED_CLIENT_IPS). | Completed.
| Read-only reader role and api_citizen view for other systems. | Completed.
LENDER SYSTEMS BACKEND (Django + DRF) CRDB-01, MoFinance-004, NMB-01, NMB-02 | Authentication:
| ● Sign-up (registration) with NIDA verification | Completed.
| ● Login (account number + PIN) | Completed.
| ● OTP | Completed.
| ● Forgot Password and Reset Password | Completed.
| ● Customer Profile | Completed.
Banking:
| ● Accounts | Completed.
| ● Deposits, withdrawals and transfers | Completed.
| ● Savings and groups | Completed.
Loans:
| ● Loan applications | Completed.
| ● Approve / reject (loan officer) | Completed.
| ● Loan schedule and repayments | Completed.
| Consent management (grant, revoke, extend). | Completed.
DAIRE integration:
| ● Push consented data to Central | Completed.
| ● Receive result broadcast from Central | Completed.
| ● Synchronization logs | Completed.
| System settings, lender credentials and audit logs. | Completed.
LENDER FRONTEND (Angular) | Customer portal:
| ● Login and sign-up pages | Completed.
| ● Forgot password and new password pages | Completed.
| ● Dashboard | Completed.
| ● Accounts and transactions pages | Completed.
| ● Loans pages | Completed.
| ● Consent page | Completed.
| ● Credit history and DAIRE score page | Completed.
| ● Notifications and profile pages | Completed.
Administration portal:
| ● Loan applications page | Completed.
| ● Customers and accounts pages | Completed.
| ● System settings page | Completed.
| Lender branding (CRDB port 4600, NMB port 4300). | Completed.
CENTRAL SYSTEM (Django + Angular) | Lenders registry and callback addresses. | Completed.
| Lender data receive API and borrower merge by borrower reference. | Completed.
| Data exchange log and routing policies. | Completed.
| Assessments (credit profile and features). | Completed.
| Broadcast of results to linked lenders. | Completed.
| Operations console: dashboard, data exchange, audit logs. | Completed.
AI ENGINE | Feature generation (11 credit features). | Completed.
| Random Forest model integration (scikit-learn, joblib). | Completed.
| AI reputation API and fallback formula. | Completed.
BLOCKCHAIN | Smart contract DaireCreditScore (dimensions D1–D5, score 300–850, risk bands). | Completed.
| Express middleware (score submit and read APIs). | Completed.
| Hardhat node deployment. | Completed.
INTEGRATION | Lender systems:
| ● Lender ↔ NIDA verification | Completed.
| ● Lender → Central data push | Completed.
| ● Central → Lender result broadcast | Completed.
| Central → AI engine. | Completed.
| Central → Blockchain. | Completed.
| End-to-end integration of all four lenders. | Not Completed.
TESTING AND QUALITY ASSUARANCE | Testing and quality assurance. | Not Completed.
DEPLOYMENT AND DELIVERY | Deployment and Delivery. | Not Completed.
MAINTENANCE AND SCALING | Maintenance and Scaling. | Not Completed.